## Three-Week Lookahead
ID | Activity | Area | Start | Finish | Predecessor / constraint | Status at 14 Sep 07:00 | Owner
A110 | MEP overhead coordination | North soffit | 2026-09-08 | 2026-09-14 | All trades confirm routing | Open: HVAC / sprinkler interface | Luis
A120 | Above-ceiling inspection | North soffit | 2026-09-17 | 2026-09-17 | A110 complete; work exposed | Booked | Luis
A130 | Soffit gypsum close-in | North soffit | 2026-09-18 | 2026-09-18 | A120 passed | Planned | Drywall
A140 | Soffit prime / first coat | North soffit | 2026-09-21 | 2026-09-22 | A130 complete and dry | Planned | Painting
M210 | Counter crates delivery | Service counter | 2026-09-15 | 2026-09-15 | Clear delivery route | Confirmed | Nina
M220 | Curved booth delivery | Dining area | 2026-09-17 | 2026-09-17 | Floor protected; route clear | Confirmed per recovery plan | Nina
M230 | Millwork installation | Counter + dining | 2026-09-18 | 2026-09-23 | M210 + M220 | Planned | Nina
F310 | Dining-area floor finish | Dining area | 2026-09-23 | 2026-09-25 | Overhead work complete | Planned | Luis
C410 | Staff training readiness | Training/community room | 2026-10-05 | 2026-10-05 | Life safety + basic furniture | Milestone | Tasha
C420 | Public opening | Whole café | 2026-10-12 | 2026-10-12 | Final approvals | Milestone | Tasha
Source note | Lookahead exported by Luis Ortega on 14 Sep 2026 at 07:00. Dates are working-plan dates, not proof that work occurred.